FR - PROJECT – NEWS APP
PLANNING
TASKS
- read tickets and list user stories
- wireframe user stories via pages / routes
- plan component tree
- plan state and context
TIMELINE
Mon AM - Planning
Mon PM - Basic landing page
Tue AM - First story and route
Tue PM - Second story and route
Wed AM – Review structure, code, naming and review plan and further stories and routes
Wed PM – implement and changes to structure and routes etc… begin further routes
Thu AM – Further routes
Thu PM – Further routes
Fri AM – Review code, structure and context, begin styling
Fri PM - Styling